## 2021 and 2022 ongoing projects
MAP Funded Projects Ongoing in 2021
Proj # | TDS | Development | Type of Work | Construction Start Date | Full Completion Date | Current Phase | Notes
9022 | 024 | Patterson | CCTV/LAC | 2016-06-13 |  | Construction | CCTV is completed but LAC work is ongoing
|  | Red Hook East | Exterior Lighting | 2022-01-15 |  | Construction | Exterior lighting work to being in Jan 22, effecting Pods, Boiler plants, etc.
|  | Red hook West | Exterior Lighting | 2022-01-15 |  | Construction | Exterior lighting work to being in Jan 22, effecting Pods, Boiler plants, etc.

## MAP Lighting
MAP Lighting
Development | Description of Work | Actual Construction Start Date | Actual Full Completion Date | Count of Fixtures | Status
Polo Grounds | Exterior Lighting | 2015-08-03 | 2016-03-01 | 315 | Completed
Bushwick | Exterior Lighting | 2015-09-09 | 2016-04-08 | 279 | Completed
Boulevard | Exterior Lighting | 2015-09-17 | 2016-06-14 | 485 | Completed
Stapleton | Exterior Lighting | 2015-11-02 | 2016-06-30 | 333 | Completed
Butler | Exterior Lighting | 2015-11-23 | 2016-09-01 | 238 | Completed
St Nicholas | Exterior Lighting | 2015-11-16 | 2016-09-23 | 268 | Completed
Castle Hill | Exterior Lighting | 2015-11-02 | 2016-11-10 | 749 | Completed
Ingersoll | Exterior Lighting | 2015-12-02 | 2016-12-19 | 523 | Completed
Van Dyke 1 | Exterior Lighting | 2016-02-16 | 2016-12-22 | 490 | Completed
Van Dyke 2 | Exterior Lighting | 2016-05-16 | 2016-12-22 | 37 | Completed
Brownsville | Exterior Lighting | 2016-06-07 | 2017-01-11 | 428 | Completed
Tompkins | Exterior Lighting | 2016-04-04 | 2017-01-13 | 324 | Completed
Wagner | Exterior Lighting | 2016-07-25 | 2017-06-09 | 422 | Completed
Patterson | Exterior Lighting | 2016-06-13 | 2017-07-13 | 452 | Completed
Queensbridge North | Exterior Lighting | 2016-10-31 | 2017-10-31 | 419 | Completed
Queensbridge South | Exterior Lighting | 2016-10-31 | 2017-10-31 | 439 | Completed
Total 16 developments (14 sites) completed |  |  |  | 6201

## MAP CCTV
MAP CCTVs
Development | Description of Work | Actual Construction Start Date | Actual Completion Date | CCTVs Completed | CCTV Status
Butler | CCTV | 2016-05-23 | 2017-01-17 | 30 | Completed
Brownsville | CCTV | 2016-01-21 | 2017-09-07 | 1 | Completed
St Nicholas | CCTV | 2016-02-29 | 2017-07-11 | 200 | Completed
Boulevard | CCTV | 2016-08-17 | 2018-04-05 | 224 | Completed
Polo Grounds | CCTV | 2016-05-23 | 2018-11-19 | 41 | Completed
Tompkins | CCTV | 2016-01-21 | 2018-05-04 | 111 | Completed
Ingersoll | CCTV | 2016-02-24 | 2017-12-15 | 279 | Completed
Van Dyke 1 | CCTV | 2016-03-29 | 2018-12-24 | 264 | Completed
Van Dyke 2 | CCTV | 2016-03-29 | 2018-12-24 | 12 | Completed
Stapleton | CCTV | 2017-06-06 | 2018-11-15 | 125 | Completed
Wagner | CCTV | 2016-03-02 | 2018-09-20 | 247 | Completed
Castle Hill | CCTV | 2016-06-01 | 2019-10-03 | 168 | Completed
Bushwick | CCTV | 2017-06-01 | 2018-09-13 | 107 | Completed
Patterson* | CCTV | 2016-06-13 | 2017-03-30 | 43 | Completed
Queensbridge North, South | CCTV | 2017-06-27 | 2020-11-04 | 469 | Completed
TOTAL CAMERAS |  |  |  | 2321
* Development has ongoing LAC work

## MAP LAC
MAP Layared Access Controls
Development | Description of Work | Actual Construction Start Date | Actual Completion Date | Doors Installed | LAC Status
Butler | LAC | 2016-05-23 | 2017-01-17 | 18 | Completed
Brownsville | LAC | 2016-01-21 | 2017-09-07 | 92 | Completed
St Nicholas | LAC | 2016-02-29 | 2018-01-10 | 28 | Completed
Boulevard | LAC | 2016-08-17 | 2018-04-17 | 36 | Completed
Polo Grounds | LAC | 2016-05-23 | 2018-11-19 | 26 | Completed
Tompkins | LAC | 2016-01-21 | 2018-05-04 | 24 | Completed
Ingersoll | LAC | 2016-02-24 | 2018-05-16 | 53 | Completed
Van Dyke 1 | LAC | 2016-03-29 | 2019-07-11 | 44 | Completed
Van Dyke 2 | LAC | 2016-03-29 | 2019-07-11 | 2 | Completed
Stapleton | LAC | 2017-06-06 | 2018-10-04 | 41 | Completed
Wagner | LAC | 2016-03-02 | 2016-09-16 | 44 | Completed
Castle Hill | LAC | 2016-06-01 | 2019-10-03 | 43 | Completed
Bushwick | LAC | 2017-06-01 | 2018-09-25 | 15 | Completed
Patterson | LAC | 2016-06-13 |  |  | In progress
Queensbridge North, South | LAC | 2017-06-27 | 2019-02-14 | 96 | Completed
TOTAL DOORS |  |  |  | 562