## developments in progress 2021
Roof Projects Ongoing in 2021
Tranche | Proj # | TDS | Development | Total Roofs Completed | Total Roofs | Complexity of Repair | Anticipated Construction Start Date | Actual Construction Start Date | Anticipated Construction Completion Date | Actual Construction Completion Date | Current Phase | City Budget | Federal Budget | Other Budget | Total Budget
2 | 7525 | 56 | BRUEKELEN | 8 | 32 | Complex |  | 2018-04-11 08:00 | 2023-04-17 08:00 |  | Construction | 32656920.98 | 35588910.58 | 0 | 68245831.56
3 | 8838 | 87 | GRANT | 10 | 10 | Complex |  | 2018-10-03 08:00 | 2022-01-13 07:00 |  | Construction | 16734065.07 | 1317037.85 | 0 | 18051102.92
3 | 9377 | 243 | BORINQUEN PLAZA I | 10 | 10 | Complex |  | 2019-04-09 08:00 | 2021-03-13 14:00 | 2021-03-12 15:00 | Closeout | 13413888.78 | 7293153.44 | 0 | 20707042.22
3 | 9861 | 502 | MORRIS II | 3 | 7 | Complex |  | 2019-05-11 08:00 | 2022-04-10 07:00 |  | Construction | 11987203.66 | 2736417.08 | 0 | 14723620.74
4 | 9928 | 29 | FARRAGUT | 4 | 10 | Complex |  | 2020-01-06 08:00 | 2022-10-07 08:00 |  | Construction | 28726623.56 | 288011.6 | 0 | 29014635.16
4 | 9923 | 62 | WASHINGTON | 0 | 14 | Complex |  | 2021-05-26 15:00 | 2023-06-01 07:00 |  | Construction | 30552386.54 | 95258.78 | 0 | 30647645.32
4 | 9924 | 8 | SOUTH JAMAICA I | 0 | 11 | Complex |  | 2021-04-19 09:00 | 2023-06-08 09:00 |  | Construction | 30111141.2 | 31026.84 | 0 | 30142168.04
4 | 9925 | 66 | SOUTH JAMAICA II | 0 | 16 | Complex |  | 2021-05-05 09:00 | 2023-06-26 09:00 |  | Construction | 25391231 | 45859.43 | 0 | 25437090.43
4 | 9926 | 100 | GOMPERS | 2 | 3 | Complex |  | 2021-05-03 14:00 | 2022-05-23 14:00 |  | Construction | 7167476.61 | 35252.67 | 0 | 7202729.28
4 | 9927 | 88 | MONROE | 0 | 13 | Complex |  | 2021-03-29 09:00 | 2023-06-10 09:00 |  | Construction | 27926650.18 | 45792.04 | 0 | 27972442.22
4 | 9998 | 159 | HOLMES | 0 | 2 | Complex |  | 2021-08-26 09:00 | 2022-10-21 09:00 |  | Construction | 6447922.25 | 0 | 0 | 6447922.25
4 | 9933 | 113 | BUTLER | 2 | 6 | Complex |  | 2021-03-29 08:00 | 2022-07-23 07:00 |  | Construction | 15026099.99 | 84754.17 | 0 | 15110854.16
4 | 9930 | 21 | MARCY | 4 | 28 | Complex |  | 2021-04-19 08:00 | 2023-10-07 08:00 |  | Construction | 48905247.19 | 276133.51 | 0 | 49181380.7
4 | 9931 | 65 | BREVOORT | 0 | 14 | Complex |  | 2021-08-23 09:00 | 2023-03-07 09:00 |  | Construction | 29921240.67 | 0 | 0 | 29921240.67
4 | 9934 | 131 | TOMPKINS | 0 | 9 | Complex |  | 2021-08-20 09:00 | 2023-01-02 09:00 |  | Construction | 24157655.26 | 45545.49 | 0 | 24203200.75
5 | 10125 | 6 | VLADECK | 0 | 20 | Complex | 2022-02-01 07:00 |  | 2024-01-31 15:00 |  | Procurement |  |  |  | 41990460
5 | 10126 | 7 | VLADECK II | 0 | 4 | Complex | 2022-02-01 08:00 |  | 2022-11-27 16:00 |  | Procurement |  |  |  | 7186736
5 | 10127 | 120 | JACKSON | 0 | 7 | Complex | 2022-11-26 14:00 |  | 2024-02-19 14:00 |  | Design |  |  |  | 10728077.5
5 | 10128 | 111 | DREW HAMILTON | 0 | 5 | Complex | 2022-08-27 07:00 |  | 2024-02-17 15:00 |  | Design |  |  |  | 24108856.94
5 | 10129 | 43 | NOSTRAND | 0 | 17 | Complex | 2022-01-31 08:00 |  | 2024-01-29 16:00 |  | Procurement |  |  |  | 31900140
5 | 10130 | 16 | BROWNSVILLE | 0 | 27 | Complex | 2022-02-26 08:00 |  | 2024-08-14 08:00 |  | Procurement |  |  |  | 49712959.68
5 | 10131 | 20 | LINCOLN | 0 | 11 | Complex | 2022-10-02 07:00 |  | 2024-05-23 15:00 |  | Design |  |  |  | 13200000
5 | 10133 | 33 | WOODSIDE | 0 | 20 | Complex | 2022-07-31 07:00 |  | 2023-12-22 15:00 |  | Procurement |  |  |  | 33481620
6 | 11897 | 61 | VAN DYKE I2 | 0 | 23 | Complex | 2023-02-08 07:00 |  | 2025-02-06 15:00 |  | Design |  |  |  | 39472390.38
6 | 11898 | 62 | DOUGLASS I | 0 | 11 | Complex | 2023-02-14 08:00 |  | 2024-11-04 16:00 |  | Design |  |  |  | 23146385.58
6 | 11899 | 582 | DOUGLASS II | 0 | 6 | Complex | 2022-11-01 07:00 |  | 2024-01-24 15:00 |  | Design |  |  |  | 10787017.02
6 | 11900 | 148 | DOUGLASS ADDITION | 0 | 1 | Complex | 2023-02-14 08:00 |  | 2023-08-12 16:00 |  | Design |  |  |  | 2175820.99
6 | 11901 | 123 | CLINTON | 0 | 8 | Complex | 2023-04-29 14:00 |  | 2024-10-20 14:00 |  | Design |  |  |  | 12705922.63
6 | 11902 | 315 | VANDALIA AVENUE | 0 | 3 | Complex | 2023-02-25 14:00 |  | 2024-02-20 14:00 |  | Design |  |  |  | 8294766.43
6 | 11903 | 223 | TELLER AVENUE-EAST 166TH STREET2 | 0 | 1 | Complex | 2022-12-27 14:00 |  | 2023-06-25 14:00 |  | Design |  |  |  | 3025674.51
6 | 11904 | 236 | COLLEGE AVE- EAST 165TH2 | 0 | 1 | Complex | 2022-12-15 07:00 |  | 2024-12-06 15:00 |  | Design |  |  |  | 2454533.77
6 | 11905 | 515 | REHAB PROGRAM (DOUGLASS REHABS) | 0 | 4 | Complex | 2023-02-01 07:00 |  | 2024-04-25 15:00 |  | Design |  |  |  | 3998475.17
6 | 11906 | 40 | GUN HILL | 0 | 6 | Complex | 2023-03-07 07:00 |  | 2024-05-30 15:00 |  | Design |  |  |  | 13392907.99
6 | 11907 | 326 | LOWER EAST SIDE I INFILL | 0 | 5 | Complex | 2022-12-07 07:00 |  | 2024-03-01 15:00 |  | Design |  |  |  | 9117434.47
6 | 11908 | 547 | HARRISON AVENUE REHAB (GROUP B) | 0 | 4 | Complex | 2022-10-08 07:00 |  | 2023-10-03 15:00 |  | Design |  |  |  | 7336170.82
6 | 11909 | 178 | WSUR (BROWNSTONES) | 0 | 36 | Complex | 2023-03-02 07:00 |  | 2026-02-28 15:00 |  | Design |  |  |  | 10144851.03
6 | 11910 | 341 | UNIVERSITY AVENUE REHAB | 0 | 4 | Complex | 2023-03-01 07:00 |  | 2024-02-23 15:00 |  | Design |  |  |  | 10701786.78
6 | 12295 | 367 | HUNTS POINT AVENUE REHAB | 0 | 13 | Complex | 2023-02-09 07:00 |  | 2024-10-31 15:00 |  | Design |  |  |  | 8616094.33
6 | 11912 | 84 | MILL BROOK (5 out of 9) | 0 | 5 | Complex | 2023-03-26 08:00 |  | 2024-06-18 08:00 |  | Design |  |  |  | 10396623.21
6 | 11913 | 192 | SEWARD PARK EXTENSION | 0 | 4 | Complex | 2023-01-18 07:00 |  | 2024-04-11 15:00 |  | Design |  |  |  | 5858846.19
6 | 11914 | 174 | WSUR (SITE C) 589 AMSTERDAM AVE | 0 | 1 | Complex | 2023-01-01 14:00 |  | 2023-06-30 14:00 |  | Design |  |  |  | 1932620.81
6 | 11915 | 256 | ATLANTIC TERMINAL SITE 4B | 0 | 1 | Complex | 2022-12-16 07:00 |  | 2023-06-13 15:00 |  | Design |  |  |  | 3862547.59
6 | 10841 | 169 | LOW HOUSES | 0 | 4 | Complex | 2022-07-23 07:00 |  | 2024-01-14 15:00 |  | Procurement |  |  |  | 9601480.94
6 | 11916 | 168 | HUGHES APARTMENTS | 0 | 4 | Complex | 2022-12-07 07:00 |  | 2023-12-02 15:00 |  | Design |  |  |  | 5710183.03
6 | 11917 | 102 | MORRIS I | 0 | 10 | Complex | 2023-01-01 14:00 |  | 2024-06-23 14:00 |  | Design |  |  |  | 16309840.43
6 | 11918 | 182 | WOODSON | 0 | 2 | Complex | 2021-12-12 07:00 |  | 2022-06-10 15:00 |  | Design |  |  |  | 5989630.58
6 | 11919 | 93 | ST. MARY'S | 0 | 2 | Complex | 2023-01-17 07:00 |  | 2024-07-10 15:00 |  | Design |  |  |  | 13961599.6
6 | 11920 | 267 | MORRISANIA AIR RIGHTS | 0 | 6 | Complex | 2023-05-02 14:00 |  | 2024-04-26 14:00 |  | Design |  |  |  | 15781069.9
6 | 11921 | 362 | LONGFELLOW AVENUE REHAB | 0 | 3 | Complex | 2022-12-10 14:00 |  | 2023-06-07 14:00 |  | Design |  |  |  | 4107951.98
6 | 11922 | 347 | HARRISON AVENUE REHAB (GROUP A) | 0 | 2 | Complex | 2022-12-07 07:00 |  | 2023-06-05 15:00 |  | Design |  |  |  | 1640437.73
6 | 10842 | 198 | BARUCH HOUSES ADDITION | 0 | 1 | Complex | 2022-06-25 07:00 |  | 2023-03-22 15:00 |  | Procurement |  |  |  | 1505979.65
6 | 11923 | 129 | MOORE | 0 | 1 | Complex | 2022-12-20 07:00 |  | 2023-06-18 15:00 |  | Design |  |  |  | 5345505.27
6 | 11924 | 287 | TWIN PARKS EAST (SITE 9) | 0 | 2 | Complex | 2023-01-01 07:00 |  | 2023-06-29 15:00 |  | Design |  |  |  | 2789087.03
6 | 11925 | 235 | BRYANT AVENUE-EAST 174TH STREET | 0 | 1 | Complex | 2022-12-06 07:00 |  | 2023-06-04 15:00 |  | Design |  |  |  | 2419510.98
6 | 11926 | 136 | FULTON | 0 | 1 | Complex | 2023-01-18 07:00 |  | 2024-10-09 15:00 |  | Design |  |  |  | 17301989.33
|  |  | Total of 55 developments in progress in 2021 | 43 | 472

## developments done prior to 2022
Roof Projects Completed Prior to January 2022
Tranche | Proj # | TDS | Development | Construction Start Date | Construction Completion Date | Number of Roofs Completed
1 | 7366 | 505 | QUEENSBRIDGE NORTH | 2015-05-28 | 2016-06-16 | 13
1 | 7365 | 005 | QUEENSBRIDGE SOUTH | 2015-05-28 | 2016-09-08 | 13
1 | 304 | 031, 085 | ALBANY I & II | 2015-08-25 | 2017-04-21 | 9
1 | 7363 | 047 | PARKSIDE | 2015-09-02 | 2017-06-30 | 14
1 | 6724 | 036 | SHEEPSHEAD BAY | 2016-03-24 | 2018-05-30 | 16
2 | 9053 | 127 | WISE TOWERS | 2018-03-27 | 2019-02-20 | 2
2 | 9053 | 124 | WHITE | 2018-03-27 | 2019-02-07 | 1
2 | 9052 | 45 | SEDGWICK | 2018-06-20 | 2019-10-31 | 7
2 | 8763 | 38 | SAINT NICHOLAS | 2018-02-01 | 2019-10-31 | 13
2 | 9055 | 96 | TILDEN | 2018-03-19 | 2019-09-30 | 8
2 | 7361 | 70 | CYPRESS HILLS | 2018-01-05 | 2019-09-30 | 15
3 | 9378 | 271 | BORINQUEN PLAZA II | 2018-09-27 | 2019-09-30 | 7
3 | 9267 | 141 | WEBSTER | 2019-02-18 | 2020-12-31 | 5
3 | 9266 | 34 | EASTCHESTER GARDENS | 2019-01-03 | 2020-12-31 | 10
3 | 9272, 10113 | 032, 157 | BRONX RIVER & BRONX RIVER ADDITION | 2018-10-11 | 2020-07-31 | 11
3 | 9318, 9319 | 92 | BAYVIEW | 2018-03-06 | 2020-10-05 | 24
3 | 9279 | 28 | MELROSE | 2018-09-25 | 2020-12-31 | 8
3 | 9377 | 243 | BORINQUEN PLAZA I | 2019-04-09 08:00 | 2021-03-13 14:00 | 10
|  |  | Total of 20 developments completed prior to 2022 |  |  | 186