## 2022 ongoing projects
NYCHA - MAP Funded Projects Ongoing in 2022
Proj # | TDS | Development | Type of Work | Construction Start Date | Full Completion Date | Current Phase | Notes
9022 | 024 | Patterson | CCTV/LAC | 2016-06-13 |  | Construction | 33 doors installed, 5 remaining. Work is completed in 13 buildings out of a total of 15 buildings, and the final tranche of work remains at two buildings (Buildings 4 and 13). The work at these two buildings involve the construction of ramps to account for a steep elevation to enter and exit the buildings. Ramps are needed both inside of the building and outside of the building entrance. These projects experienced delays in the design phase, as more work was required than originally anticipated, and the team had extensive engagement with DOB to obtain final approvals. Doors will be installed after the ramps are completed, and we expect the project will be closed out by the end of 2023.
10287, 8307 | 004 | Red Hook East | Exterior Lighting | 2022-01-15 |  | Construction | Anticipated completion of August 2023. Exterior lighting effecting pods, boiler plants, etc.
12967, 8308 | 079 | Red hook West | Exterior Lighting | 2022-01-15 |  | Construction | Anticipated completion of August 2023. Exterior lighting effecting pods, boiler plants, etc.

## MAP Lighting
NYCHA - MAP Lighting
Development | Description of Work | Actual Construction Start Date | Actual Full Completion Date | Count of Fixtures | Status
Polo Grounds | Exterior Lighting | 2015-08-03 | 2016-03-01 | 315 | Completed
Bushwick | Exterior Lighting | 2015-09-09 | 2016-04-08 | 279 | Completed
Boulevard | Exterior Lighting | 2015-09-17 | 2016-06-14 | 485 | Completed
Stapleton | Exterior Lighting | 2015-11-02 | 2016-06-30 | 333 | Completed
Butler | Exterior Lighting | 2015-11-23 | 2016-09-01 | 238 | Completed
St Nicholas | Exterior Lighting | 2015-11-16 | 2016-09-23 | 268 | Completed
Castle Hill | Exterior Lighting | 2015-11-02 | 2016-11-10 | 749 | Completed
Ingersoll | Exterior Lighting | 2015-12-02 | 2016-12-19 | 523 | Completed
Van Dyke 1 | Exterior Lighting | 2016-02-16 | 2016-12-22 | 490 | Completed
Van Dyke 2 | Exterior Lighting | 2016-05-16 | 2016-12-22 | 37 | Completed
Brownsville | Exterior Lighting | 2016-06-07 | 2017-01-11 | 428 | Completed
Tompkins | Exterior Lighting | 2016-04-04 | 2017-01-13 | 324 | Completed
Wagner | Exterior Lighting | 2016-07-25 | 2017-06-09 | 422 | Completed
Patterson | Exterior Lighting | 2016-06-13 | 2017-07-13 | 452 | Completed
Queensbridge North | Exterior Lighting | 2016-10-31 | 2017-10-31 | 419 | Completed
Queensbridge South | Exterior Lighting | 2016-10-31 | 2017-10-31 | 439 | Completed
Total 16 developments (14 sites) completed |  |  |  | 6201

## MAP CCTV
NYCHA - MAP CCTVs
Development | Description of Work | Actual Construction Start Date | Actual Completion Date | CCTVs Completed | CCTV Status
Butler | CCTV | 2016-05-23 | 2017-01-17 | 30 | Completed
Brownsville | CCTV | 2016-01-21 | 2017-09-07 | 1 | Completed
St Nicholas | CCTV | 2016-02-29 | 2017-07-11 | 200 | Completed
Boulevard | CCTV | 2016-08-17 | 2018-04-05 | 224 | Completed
Polo Grounds | CCTV | 2016-05-23 | 2018-11-19 | 41 | Completed
Tompkins | CCTV | 2016-01-21 | 2018-05-04 | 111 | Completed
Ingersoll | CCTV | 2016-02-24 | 2017-12-15 | 279 | Completed
Van Dyke 1 | CCTV | 2016-03-29 | 2018-12-24 | 264 | Completed
Van Dyke 2 | CCTV | 2016-03-29 | 2018-12-24 | 12 | Completed
Stapleton | CCTV | 2017-06-06 | 2018-11-15 | 125 | Completed
Wagner | CCTV | 2016-03-02 | 2018-09-20 | 247 | Completed
Castle Hill | CCTV | 2016-06-01 | 2019-10-03 | 168 | Completed
Bushwick | CCTV | 2017-06-01 | 2018-09-13 | 107 | Completed
Patterson* | CCTV | 2016-06-13 | 2017-03-30 | 43 | Completed
Queensbridge North, South | CCTV | 2017-06-27 | 2020-11-04 | 469 | Completed
Total Cameras |  |  |  | 2321
* Development has ongoing LAC work

## MAP LAC
NYCHA - MAP Layered Access Controls (LAC)
Development | Description of Work | Actual Construction Start Date | Actual Completion Date | Doors Installed | LAC Status
Butler | LAC | 2016-05-23 | 2017-01-17 | 18 | Completed
Brownsville | LAC | 2016-01-21 | 2017-09-07 | 92 | Completed
St Nicholas | LAC | 2016-02-29 | 2018-01-10 | 28 | Completed
Boulevard | LAC | 2016-08-17 | 2018-04-17 | 36 | Completed
Polo Grounds | LAC | 2016-05-23 | 2018-11-19 | 26 | Completed
Tompkins | LAC | 2016-01-21 | 2018-05-04 | 24 | Completed
Ingersoll | LAC | 2016-02-24 | 2018-05-16 | 53 | Completed
Van Dyke 1 | LAC | 2016-03-29 | 2019-07-11 | 44 | Completed
Van Dyke 2 | LAC | 2016-03-29 | 2019-07-11 | 2 | Completed
Stapleton | LAC | 2017-06-06 | 2018-10-04 | 41 | Completed
Wagner | LAC | 2016-03-02 | 2016-09-16 | 44 | Completed
Castle Hill | LAC | 2016-06-01 | 2019-10-03 | 43 | Completed
Bushwick | LAC | 2017-06-01 | 2018-09-25 | 15 | Completed
Patterson | LAC | 2016-06-13 |  | 33 | In progress
Queensbridge North, South | LAC | 2017-06-27 | 2019-02-14 | 96 | Completed
Total Doors |  |  |  | 595