## Summary
NYCHA - MAP Roof Repair
The MAP Roof Repair effort entails 657 total planned roof replacements.
'developments in progress 2022' represent any development that was undergoing active work at any point in 2022.
'developments done prior to 2023' represent any development where the roof repairs were complete by December 31, 2022.

## developments in progress 2022
Roof Projects Ongoing in 2022
Tranche | Proj # | TDS | Development* | Total Roofs Completed | Total Roofs | Complexity of Repair | Current Phase | Anticipated Construction Start Date (Baseline) | Actual Construction Start Date | Anticipated Construction Completion Date (Baseline) | Actual Construction Completion Date | City Budget | Federal Budget | State Budget | Other Budget | Total Budget
2 | 7525 | 56 | BRUEKELEN | 11 | 32 | Complex | Construction |  | 2018-04-11 | 2023-04-16 |  | 34736378 | 35937935 | 0 | 0 | 70674313
3 | 8838 | 87 | GRANT | 10 | 10 | Complex | Closeout |  | 2018-10-03 |  | 2022-02-11 | 16626558 | 1176938 | 0 | 0 | 17803496
3 | 9861 | 502 | MORRIS II | 7 | 7 | Complex | Closeout |  | 2019-05-11 |  | 2022-10-28 | 13152820 | 2736417 | 0 | 0 | 15889237
4 | 9933 | 113 | BUTLER | 6 | 6 | Complex | Construction |  | 2021-03-29 |  | 2022-12-31 | 15026100 | 84754 | 0 | 0 | 15110854
4 | 9928 | 29 | FARRAGUT | 10 | 10 | Complex | Closeout |  | 2020-01-06 |  | 2022-10-03 | 28726624 | 286179 | 0 | 0 | 29012803
4 | 9931 | 65 | BREVOORT | 8 | 14 | Complex | Construction |  | 2021-08-23 | 2023-03-06 |  | 29497591 | 0 | 0 | 0 | 29497591
4 | 9934 | 131 | TOMPKINS | 3 | 8 | Complex | Construction |  | 2021-08-20 | 2023-03-06 |  | 22310713 | 43713 | 0 | 0 | 22354426
4 | 9926 | 100 | GOMPERS | 3 | 3 | Complex | Closeout |  | 2021-05-03 |  | 2022-10-26 | 7167476 | 35253 | 0 | 0 | 7202729
4 | 9923 | 62 | WASHINGTON | 5 | 14 | Complex | Construction |  | 2021-05-26 | 2023-05-31 |  | 30495157 | 95259 | 0 | 0 | 30590416
4 | 9927 | 88 | MONROE | 13 | 13 | Complex | Construction |  | 2021-03-29 |  | 2022-12-31 | 27926650 | 45792 | 0 | 0 | 27972442
4 | 9932 | 1 | FIRST HOUSES | 0 | 10 | Complex | Design | 2021-12-18 |  | 2023-06-10 |  | 17910200 | 185553 | 0 | 432500 | 18528253
4 | 9924 | 8 | SOUTH JAMAICA I | 11 | 11 | Complex | Construction |  | 2021-04-19 |  | 2022-12-31 | 30111141 | 31027 | 0 | 0 | 30142168
4 | 9925 | 66 | SOUTH JAMAICA II | 11 | 16 | Complex | Construction |  | 2021-05-05 | 2023-08-20 |  | 25391231 | 45859 | 0 | 0 | 25437090
4 | 9998 | 159 | HOLMES | 0 | 2 | Complex | Construction |  | 2021-08-26 | 2023-09-05 |  | 6447922 | 1127156 | 0 | 0 | 7575078
4 | 9930 | 21 | MARCY | 21 | 28 | Complex | Construction |  | 2021-04-19 | 2023-11-29 |  | 48905247 | 300009 | 0 | 0 | 49205256
5 | 10126 | 7 | VLADECK II | 1 | 4 | Complex | Construction |  | 2022-06-30 | 2023-03-19 |  | 4750298 | 29322 | 0 | 0 | 4779620
5 | 10133 | 33 | WOODSIDE | 0 | 20 | Complex | Construction |  | 2022-11-14 | 2023-12-20 |  | 23763606 | 130775 | 0 | 0 | 23894381
5 | 10129 | 43 | NOSTRAND | 2 | 17 | Complex | Construction |  | 2022-06-17 | 2023-12-25 |  | 39403233 | 113157 | 0 | 0 | 39516390
5 | 10127 | 120 | JACKSON | 0 | 7 | Complex | Procurement | 2022-12-23 |  | 2024-03-16 |  | 15821714 | 37731 | 0 | 0 | 15859445
5 | 10131 | 20 | LINCOLN | 0 | 11 | Complex | Design | 2022-08-14 |  | 2024-04-04 |  | 703327 | 125785 | 0 | 0 | 829112
5 | 10125 | 6 | VLADECK | 2 | 20 | Complex | Construction |  | 2022-06-30 | 2024-05-22 |  | 25033008 | 134147 | 0 | 0 | 25167155
5 | 10128 | 111 | DREW HAMILTON | 0 | 5 | Complex | Procurement | 2022-12-31 |  | 2024-06-23 |  | 633500 | 4082 | 0 | 24961 | 662543
5 | 10130 | 16 | BROWNSVILLE | 4 | 27 | Complex | Construction |  | 2022-06-16 | 2024-07-14 |  | 53413640 | 166635 | 0 | 0 | 53580275
6 | 11903 | 223 | TELLER AVENUE-EAST 166TH STREET2 | 0 | 1 | Complex | Design | 2022-09-13 |  | 2023-03-11 |  | 80000 | 5780 | 0 | 0 | 85780
6 | 11904 | 236 | COLLEGE AVE- EAST 165TH2 | 0 | 1 | Complex | Design | 2021-03-22 |  | 2023-03-14 |  | 0 | 9080 | 0 | 0 | 9080
6 | 10842 | 198 | BARUCH HOUSES ADDITION | 0 | 1 | Complex | Procurement | 2022-06-25 |  | 2023-03-22 |  | 0 | 0 | 0 | 0 | 0
6 | 11925 | 235 | BRYANT AVENUE-EAST 174TH STREET | 0 | 1 | Complex | Procurement | 2022-12-02 |  | 2023-05-31 |  | 78000 | 14732 | 0 | 0 | 92732
6 | 11921 | 362 | LONGFELLOW AVENUE REHAB | 0 | 3 | Complex | Design | 2022-12-10 |  | 2023-06-07 |  | 120000 | 11170 | 0 | 0 | 131170
6 | 11918 | 182 | WOODSON | 0 | 2 | Complex | Design | 2022-12-12 |  | 2023-06-10 |  | 91836 | 34795 | 0 | 0 | 126631
6 | 11915 | 256 | ATLANTIC TERMINAL SITE 4B | 0 | 1 | Complex | Design | 2023-01-25 |  | 2023-07-25 |  | 57659 | 26204 | 0 | 0 | 83863
6 | 11900 | 148 | DOUGLASS ADDITION | 0 | 1 | Complex | Design | 2023-02-04 |  | 2023-08-02 |  | 157000 | 0 | 0 | 0 | 157000
6 | 11923 | 129 | MOORE | 0 | 1 | Complex | Design | 2023-02-11 |  | 2023-08-11 |  | 279550 | 9450 | 0 | 0 | 289000
6 | 11922 | 347 | HARRISON AVENUE REHAB (GROUP A) | 0 | 2 | Complex | Design | 2023-02-24 |  | 2023-08-23 |  | 126000 | 5184 | 0 | 0 | 131184
6 | 11914 | 174 | WSUR (SITE C) 589 AMSTERDAM AVE | 0 | 1 | Complex | Design | 2023-03-28 |  | 2023-09-24 |  | 155000 | 0 | 0 | 0 | 155000
6 | 11924 | 287 | TWIN PARKS EAST (SITE 9) | 0 | 2 | Complex | Procurement | 2023-04-17 |  | 2023-10-14 |  | 78000 | 9115 | 0 | 0 | 87115
6 | 11902 | 315 | VANDALIA AVENUE | 0 | 3 | Complex | Design | 2022-11-12 |  | 2023-11-06 |  | 329700 | 0 | 0 | 0 | 329700
6 | 10841 | 169 | LOW HOUSES | 0 | 4 | Complex | Construction |  | 2022-12-07 | 2023-12-19 |  | 11144010 | 0 | 0 | 0 | 11144010
6 | 11920 | 267 | MORRISANIA AIR RIGHTS | 0 | 6 | Complex | Design | 2023-01-16 |  | 2024-01-11 |  | 287000 | 26395 | 0 | 0 | 313395
6 | 11899 | 582 | DOUGLASS II | 0 | 6 | Complex | Design | 2022-11-04 |  | 2024-01-27 |  | 551000 | 0 | 0 | 0 | 551000
6 | 11910 | 341 | UNIVERSITY AVENUE REHAB | 0 | 4 | Complex | Design | 2023-02-06 |  | 2024-01-31 |  | 316000 | 68347 | 0 | 0 | 384347
6 | 11908 | 547 | HARRISON AVENUE REHAB (GROUP B) | 0 | 4 | Complex | Design | 2023-04-07 |  | 2024-04-01 |  | 434000 | 25616 | 0 | 0 | 459616
6 | 11913 | 192 | SEWARD PARK EXTENSION | 0 | 4 | Complex | Design | 2023-01-18 |  | 2024-04-11 |  | 282500 | 26000 | 0 | 0 | 308500
6 | 11905 | 515 | REHAB PROGRAM (DOUGLASS REHABS) | 0 | 4 | Complex | Design | 2023-02-02 |  | 2024-04-26 |  | 319000 | 19050 | 0 | 0 | 338050
6 | 11916 | 168 | HUGHES APARTMENTS | 0 | 4 | Complex | Design | 2023-05-08 |  | 2024-05-02 |  | 316392 | 0 | 0 | 0 | 316392
6 | 11907 | 326 | LOWER EAST SIDE I INFILL | 0 | 5 | Complex | Design | 2023-04-10 |  | 2024-07-03 |  | 513000 | 0 | 0 | 0 | 513000
6 | 11919 | 93 | ST. MARY'S | 0 | 2 | Complex | Design | 2023-01-17 |  | 2024-07-10 |  | 370000 | 60855 | 0 | 0 | 430855
6 | 11917 | 102 | MORRIS I | 0 | 10 | Complex | Design | 2023-01-18 |  | 2024-07-10 |  | 491650 | 9500 | 0 | 0 | 501150
6 | 11912 | 84 | MILL BROOK (5 out of 9) | 0 | 5 | Complex | Design | 2023-07-02 |  | 2024-09-24 |  | 565120 | 9150 | 0 | 0 | 574270
6 | 11906 | 40 | GUN HILL | 0 | 6 | Complex | Design | 2023-07-06 |  | 2024-09-28 |  | 424000 | 33050 | 0 | 0 | 457050
6 | 11901 | 123 | CLINTON | 0 | 8 | Complex | Procurement | 2023-04-29 |  | 2024-10-20 |  | 595000 | 0 | 0 | 0 | 595000
6 | 11898 | 62 | DOUGLASS I | 0 | 11 | Complex | Design | 2023-02-04 |  | 2024-10-25 |  | 1006600 | 0 | 0 | 0 | 1006600
6 | 12295 | 367 | HUNTS POINT AVENUE REHAB | 0 | 13 | Complex | Design | 2023-02-09 |  | 2024-10-31 |  | 340000 | 82550 | 0 | 0 | 422550
6 | 11926 | 136 | FULTON | 0 | 1 | Complex | Design | 2023-03-10 |  | 2024-11-29 |  | 419948 | 550263 | 0 | 0 | 970211
6 | 11897 | 61 | VAN DYKE I & II | 0 | 23 | Complex | Design | 2023-02-06 |  | 2025-02-04 |  | 688238 | 0 | 0 | 0 | 688238
6 | 11909 | 178 | WSUR (BROWNSTONES) | 0 | 36 | Complex | Design | 2023-06-13 |  | 2026-06-11 |  | 396025 | 111748 | 0 | 0 | 507773
|  |  | Total | 128 | 471
NOTES:
* Roofs repairs were in progress across 56 developments in 2022, and were grouped together in 55 unique project numbers

## developments done prior to 2023
Roof Projects Completed Prior to January 2023
Tranche | Proj # | TDS | Development* | Construction Start Date | Construction Completion Date | Number of Roofs Completed | Number of Roofs Remaining | Total Roofs in Project
1 | 7366 | 505 | QUEENSBRIDGE NORTH | 2015-05-28 | 2016-06-16 | 13 | 0 | 13
1 | 7365 | 005 | QUEENSBRIDGE SOUTH | 2015-05-28 | 2016-09-08 | 13 | 0 | 13
1 | 304 | 031, 085 | ALBANY I & II | 2015-08-25 | 2017-04-21 | 9 | 0 | 9
1 | 7363 | 047 | PARKSIDE | 2015-09-02 | 2017-06-30 | 14 | 0 | 14
1 | 6724 | 036 | SHEEPSHEAD BAY | 2016-03-24 | 2018-05-30 | 16 | 0 | 16
2 | 9053 | 127 | WISE TOWERS | 2018-03-27 | 2019-02-20 | 2 | 0 | 2
2 | 9053 | 124 | WHITE | 2018-03-27 | 2019-02-07 | 1 | 0 | 1
2 | 9052 | 45 | SEDGWICK | 2018-06-20 | 2019-10-31 | 7 | 0 | 7
2 | 8763 | 38 | SAINT NICHOLAS | 2018-02-01 | 2019-10-31 | 13 | 0 | 13
2 | 9055 | 96 | TILDEN | 2018-03-19 | 2019-09-30 | 8 | 0 | 8
2 | 7361 | 70 | CYPRESS HILLS | 2018-01-05 | 2019-09-30 | 15 | 0 | 15
3 | 9378 | 271 | BORINQUEN PLAZA II | 2018-09-27 | 2019-09-30 | 7 | 0 | 7
3 | 9267 | 141 | WEBSTER | 2019-02-18 | 2020-12-31 | 5 | 0 | 5
3 | 9266 | 34 | EASTCHESTER GARDENS | 2019-01-03 | 2020-12-31 | 10 | 0 | 10
3 | 9272, 10113 | 032, 157 | BRONX RIVER & BRONX RIVER ADDITION | 2018-10-11 | 2020-07-31 | 11 | 0 | 11
3 | 9318, 9319 | 92 | BAYVIEW | 2018-03-06 | 2020-10-05 | 24 | 0 | 24
3 | 9279 | 28 | MELROSE | 2018-09-25 | 2020-12-31 | 8 | 0 | 8
3 | 9377 | 243 | BORINQUEN PLAZA I | 2019-04-09 08:00 | 2021-03-13 14:00 | 10 | 0 | 10
3 | 8838 | 87 | GRANT | 2018-10-03 | 2022-02-11 | 10 | 0 | 10
3 | 9861 | 502 | MORRIS II | 2019-05-11 | 2022-10-28 | 7 | 0 | 7
4 | 9928 | 29 | FARRAGUT | 2020-01-06 | 2022-10-03 | 10 | 0 | 10
4 | 9926 | 100 | GOMPERS | 2021-05-03 | 2022-10-26 | 3 | 0 | 3
4 | 9924 | 8 | SOUTH JAMAICA I | 2021-04-19 | 2022-12-31 | 11 | 0 | 11
4 | 9933 | 113 | BUTLER | 2021-03-29 | 2022-12-31 | 6 | 0 | 6
4 | 9927 | 88 | MONROE | 2021-03-29 | 2022-12-31 | 13 | 0 | 13
|  |  | Total |  |  | 246 | 0 | 246
NOTES:
* Roofs repairs have been completed in a total of 27 developments