## Summary
The Mayor's Action Plan includes Lighting projects at 16 NYCHA Developments, and CCTV and Layered Access Control (LAC) projects at 16 developments. All but one 1 LAC project, was completed before 2023. All MAP Projects were completed as of 2023. Project information for these projects is provided on the following sheets.

## MAP Lighting
MAP Lighting
Development | Count of Fixtures | Actual Construction Start Date | Construction Completion Date (Actual or Forecast) | Current Phase
Polo Grounds | 315 | 2015-08-03 | 2016-03-01 | Complete
Bushwick | 279 | 2015-09-09 | 2016-04-08 | Complete
Boulevard | 485 | 2015-09-17 | 2016-06-14 | Complete
Stapleton | 333 | 2015-11-02 | 2016-06-30 | Complete
Butler | 238 | 2015-11-23 | 2016-09-01 | Complete
St Nicholas | 268 | 2015-11-16 | 2016-09-23 | Complete
Castle Hill | 749 | 2015-11-02 | 2016-11-10 | Complete
Ingersoll | 523 | 2015-12-02 | 2016-12-19 | Complete
Van Dyke 1 | 490 | 2016-02-16 | 2016-12-22 | Complete
Van Dyke 2 | 37 | 2016-05-16 | 2016-12-22 | Complete
Brownsville | 428 | 2016-06-07 | 2017-01-11 | Complete
Tompkins | 324 | 2016-04-04 | 2017-01-13 | Complete
Wagner | 422 | 2016-07-25 | 2017-06-09 | Complete
Patterson | 452 | 2016-06-13 | 2017-07-13 | Complete
Queensbridge North | 419 | 2016-10-31 | 2017-10-31 | Complete
Queensbridge South | 439 | 2016-10-31 | 2017-10-31 | Complete
Total | 6201

## MAP CCTV
MAP CCTVs
Development | CCTVs Completed | Actual Construction Start Date | Construction Completion Date (Actual or Forecast) | Current Phase
Butler | 30 | 2016-05-23 | 2017-01-17 | Complete
Brownsville | 1 | 2016-01-21 | 2017-09-07 | Complete
St Nicholas | 200 | 2016-02-29 | 2017-07-11 | Complete
Boulevard | 224 | 2016-08-17 | 2018-04-05 | Complete
Polo Grounds | 41 | 2016-05-23 | 2018-11-19 | Complete
Tompkins | 111 | 2016-01-21 | 2018-05-04 | Complete
Ingersoll | 279 | 2016-02-24 | 2017-12-15 | Complete
Van Dyke 1 | 264 | 2016-03-29 | 2018-12-24 | Complete
Van Dyke 2 | 12 | 2016-03-29 | 2018-12-24 | Complete
Stapleton | 125 | 2017-06-06 | 2018-11-15 | Complete
Wagner | 247 | 2016-03-02 | 2018-09-20 | Complete
Castle Hill | 168 | 2016-06-01 | 2019-10-03 | Complete
Bushwick | 107 | 2017-06-01 | 2018-09-13 | Complete
Patterson | 43 | 2016-06-13 | 2017-03-30 | Complete
Queensbridge North, South | 469 | 2017-06-27 | 2020-11-04 | Complete
TOTAL CAMERAS | 2321

## MAP LAC
MAP Layered Access Controls
Development | Doors Installed | Actual Construction Start Date | Construction Completion Date (Actual or Forecast) | Current Phase
Butler | 18 | 2016-05-23 | 2017-01-17 | Complete
Brownsville | 92 | 2016-01-21 | 2017-09-07 | Complete
St Nicholas | 28 | 2016-02-29 | 2018-01-10 | Complete
Boulevard | 36 | 2016-08-17 | 2018-04-17 | Complete
Polo Grounds | 26 | 2016-05-23 | 2018-11-19 | Complete
Tompkins | 24 | 2016-01-21 | 2018-05-04 | Complete
Ingersoll | 53 | 2016-02-24 | 2018-05-16 | Complete
Van Dyke 1 | 44 | 2016-03-29 | 2019-07-11 | Complete
Van Dyke 2 | 2 | 2016-03-29 | 2019-07-11 | Complete
Stapleton | 41 | 2017-06-06 | 2018-10-04 | Complete
Wagner | 44 | 2016-03-02 | 2016-09-16 | Complete
Castle Hill | 43 | 2016-06-01 | 2019-10-03 | Complete
Bushwick | 15 | 2017-06-01 | 2018-09-25 | Complete
Patterson | 50 | 2016-06-13 | 2023-11-30 | Complete
Queensbridge North, South | 96 | 2017-06-27 | 2019-02-14 | Complete
TOTAL DOORS | 612