## Summary
NYCHA - Roof Replacement Program
The Roof Replacement Program entails 701 total roof replacements and repairs through CFY 2028, utilizing a total of $1billion of City capital funds as well as other funding sources. 415 roofs have been replaced as of December 31, 2023, including 121 completed in 2023. 90 roofs are still in construction as of December 31, 2023. Project information for these 505 roofs in total is provided on the following sheet.

## Roofs Done or in Construction
Tranche | Proj # | TDS | Development | Roofs Completed | Roofs Remaining | Total Roofs To Be Replaced | Complexity of Repair | Construction Start Date | Construction Completion Date (Actual or Forecast) | Current Phase | City Budget | Federal Budget | Total Budget
1 | 7366 | 505 | QUEENSBRIDGE NORTH | 13 | 0 | 13 | Complex | 2015-05-28 | 2016-06-16 | Complete | 28123610.43 | 16091807.64 | 44215418.07
1 | 7365 | 005 | QUEENSBRIDGE SOUTH | 13 | 0 | 13 | Complex | 2015-05-28 | 2016-09-08 | Complete | 27802028.74 | 20844153.4 | 48646182.14
1 | 304 | 31 | ALBANY | 6 | 0 | 6 | Complex | 2015-08-25 | 2017-04-21 | Complete | 9870447 | 39082058.52 | 48952505.52
1 | 304 | 85 | ALBANY II | 3 | 0 | 3 | Complex | 2015-08-25 | 2017-04-21 | Complete | 0 | 0 | 0
1 | 7363 | 047 | PARKSIDE | 14 | 0 | 14 | Complex | 2015-09-02 | 2017-06-30 | Complete | 14441871.29 | 20547049.68 | 34988920.97
1 | 6724 | 036 | SHEEPSHEAD BAY | 16 | 0 | 16 | Complex | 2016-03-24 | 2018-05-30 | Complete | 14446413.08 | 1826345.88 | 16272758.96
2 | 9053 | 127 | WISE TOWERS | 2 | 0 | 2 | Complex | 2018-03-27 | 2019-02-20 | Complete | 7226030.81 | 0 | 7226030.81
2 | 9053 | 124 | WHITE | 1 | 0 | 1 | Complex | 2018-03-27 | 2019-02-07 | Complete | 0 | 0 | 0
2 | 9052 | 45 | SEDGWICK | 7 | 0 | 7 | Complex | 2018-06-20 | 2019-10-31 | Complete | 8808119.61 | 0 | 8808119.61
2 | 8763 | 38 | SAINT NICHOLAS | 13 | 0 | 13 | Complex | 2018-02-01 | 2019-10-31 | Complete | 12723983.79 | 16147.62 | 12740131.41
2 | 9055 | 96 | TILDEN | 8 | 0 | 8 | Complex | 2018-03-19 | 2019-09-30 | Complete | 9438882.24 | 0 | 9438882.24
2 | 7361 | 70 | CYPRESS HILLS | 15 | 0 | 15 | Complex | 2018-01-05 | 2019-09-30 | Complete | 15847397.27 | 0 | 15847397.27
2 | 7525 | 56 | BRUEKELEN | 16 | 16 | 32 | Complex | 2018-04-11 | 2024-07-31 | Construction | 34736376.76 | 38937934.58 | 73674311.34
3 | 9378 | 271 | BORINQUEN PLAZA II | 7 | 0 | 7 | Complex | 2018-09-27 | 2019-09-30 | Complete | 7953742.95 | 22871.75 | 7976614.7
3 | 9267 | 141 | WEBSTER | 5 | 0 | 5 | Complex | 2019-02-18 | 2020-12-31 | Complete | 4769257.41 | 2223334.55 | 6992591.96
3 | 9266 | 34 | EASTCHESTER GARDENS | 10 | 0 | 10 | Complex | 2019-01-03 | 2020-12-31 | Complete | 12259001.99 | 9971972.44 | 22230974.43
3 | 9272 | 32 | BRONX RIVER | 11 | 0 | 11 | Complex | 2018-10-11 | 2020-07-31 | Complete | 18519711.55 | 1136330.68 | 19656042.23
3 | 9318, 9319 | 92 | BAYVIEW | 24 | 0 | 24 | Complex | 2018-03-06 | 2020-10-05 | Complete | 19628472.57 | 0 | 51413114.39
3 | 9279 | 28 | MELROSE | 8 | 0 | 8 | Complex | 2018-09-25 | 2020-12-31 | Complete | 11082441.06 | 5245328.75 | 16327769.81
3 | 9377 | 243 | BORINQUEN PLAZA I | 10 | 0 | 10 | Complex | 2019-04-09 08:00 | 2021-03-13 14:00 | Complete | 6027808.19 | 5891669.03 | 11919477.22
3 | 8838 | 87 | GRANT | 10 | 0 | 10 | Complex | 2018-10-03 | 2022-02-11 | Complete | 14984454.5 | 974451.08 | 15958905.58
3 | 9861 | 502 | MORRIS II | 7 | 0 | 7 | Complex | 2019-05-11 | 2022-10-28 | Complete | 8264826.32 | 2575497.07 | 10840323.39
4 | 9928 | 29 | FARRAGUT | 10 | 0 | 10 | Complex | 2020-01-06 | 2022-10-03 | Complete | 23874953.36 | 181147.06 | 24056100.42
4 | 9926 | 100 | GOMPERS | 3 | 0 | 3 | Complex | 2021-05-03 | 2022-10-26 | Complete | 6491477.6 | 7994.49 | 6499472.09
4 | 9923 | 62 | WASHINGTON | 14 | 0 | 14 | Complex | 2021-05-26 | 2023-12-14 | Complete | 30039065.32 | 95258.78 | 30134324.1
4 | 9924 | 8 | SOUTH JAMAICA I | 11 | 0 | 11 | Complex | 2021-04-19 | 2023-03-15 | Complete | 27418344.2 | 31026.84 | 27449371.04
4 | 9925 | 66 | SOUTH JAMAICA II | 16 | 0 | 16 | Complex | 2021-05-05 | 2023-06-23 | Complete | 23356299.7 | 45859.43 | 23402159.13
4 | 9927 | 88 | MONROE | 13 | 0 | 13 | Complex | 2021-03-29 | 2023-06-09 | Complete | 25801960.18 | 45792.04 | 25847752.22
4 | 9998 | 159 | HOLMES | 2 | 0 | 2 | Complex | 2021-08-26 | 2023-09-15 | Complete | 6214525.25 | 1127156 | 7341681.25
4 | 9933 | 113 | BUTLER | 6 | 0 | 6 | Complex | 2021-03-29 | 2023-03-16 | Complete | 13917398.25 | 84754.17 | 14002152.42
4 | 9930 | 21 | MARCY | 28 | 0 | 28 | Complex | 2021-04-19 | 2023-11-29 | Complete | 44733247.19 | 300008.62 | 45033255.81
4 | 9931 | 65 | BREVOORT | 13 | 0 | 13 | Complex | 2021-08-23 | 2023-10-31 | Complete | 27414240.67 | 0 | 27414240.67
4 | 9932 | 1 | FIRST HOUSES | 1 | 7 | 8 | Complex | 2023-05-08 | 2025-09-15 | Construction | 14294200 | 10820309.37 | 25114509.37
4 | 9934 | 131 | TOMPKINS | 8 | 0 | 8 | Complex | 2021-08-20 | 2024-04-14 | Construction | 18936986.76 | 43713 | 18980699.76
5 | 10125 | 6 | VLADECK | 20 | 0 | 20 | Complex | 2022-06-30 | 2024-03-30 | Construction | 22109008.23 | 134146.97 | 22243155.2
5 | 10126 | 7 | VLADECK II | 4 | 0 | 4 | Complex | 2022-06-30 | 2023-06-29 | Complete | 3635298.19 | 29321.88 | 3664620.07
5 | 10127 | 120 | JACKSON | 1 | 6 | 7 | Complex | 2023-04-27 | 2025-08-02 | Construction | 14575449.5 | 92253.44 | 14667702.94
5 | 10128 | 111 | DREW HAMILTON | 5 | 0 | 5 | Complex | 2023-05-16 | 2024-11-08 | Construction | 16826656.07 | 4082.48 | 16830738.55
5 | 10129 | 43 | NOSTRAND | 11 | 6 | 17 | Complex | 2022-06-17 | 2024-06-25 | Construction | 37002683.81 | 113157.04 | 37115840.85
5 | 10130 | 16 | BROWNSVILLE | 20 | 7 | 27 | Complex | 2022-06-16 | 2024-12-02 | Construction | 49242592.42 | 4463354.32 | 53705946.74
5 | 10133 | 33 | WOODSIDE | 6 | 3 | 9 | Complex | 2022-11-14 | 2025-01-27 | Construction | 27662261.54 | 130774.89 | 27793036.43
6 | 11900 | 148 | DOUGLASS ADDITION | 0 | 1 | 1 | Complex | 2023-09-21 | 2025-08-09 | Construction | 4154154 | 0 | 4154154
6 | 11901 | 123 | CLINTON | 0 | 7 | 7 | Complex | 2023-07-22 | 2025-09-06 | Construction | 14867353.1 | 0 | 14867353.1
6 | 11903 | 223 | TELLER AVENUE-EAST 166TH STREET2 | 0 | 1 | 1 | Complex | 2023-11-22 | 2025-07-29 | Construction | 4390000 | 5780 | 4395780
6 | 11904 | 236 | COLLEGE AVE- EAST 165TH2 | 0 | 1 | 1 | Complex | 2023-12-05 | 2025-10-18 | Construction | 3294769.47 | 9080 | 3303849.47
6 | 11905 | 515 | REHAB PROGRAM (DOUGLASS REHABS) | 0 | 3 | 3 | Complex | 2023-11-27 | 2025-08-09 | Construction | 5873140.71 | 21185.45 | 5894326.16
6 | 11910 | 341 | UNIVERSITY AVENUE REHAB | 0 | 4 | 4 | Complex | 2023-09-22 | 2025-08-21 | Construction | 9429637 | 68347 | 9497984
6 | 12295 | 367 | HUNTS POINT AVENUE REHAB | 0 | 8 | 8 | Complex | 2023-09-18 | 2025-06-26 | Construction | 18035280.09 | 82550 | 18117830.09
6 | 11914 | 174 | WSUR (SITE C) 589 AMSTERDAM AVE | 0 | 1 | 1 | Complex | 2023-09-19 | 2025-05-01 | Construction | 4580000 | 0 | 4580000
6 | 10841 | 169 | LOW HOUSES | 4 | 0 | 4 | Complex | 2022-12-07 | 2023-12-19 | Construction | 11144010 | 0 | 11144010
6 | 11916 | 168 | HUGHES APARTMENTS | 0 | 4 | 4 | Complex | 2023-12-27 | 2026-04-07 | Construction | 9448392 | 0 | 9448392
6 | 11919 | 93 | ST. MARY'S | 0 | 6 | 6 | Complex | 2023-12-26 | 2025-08-15 | Construction | 11568000 | 60855 | 11628855
6 | 11920 | 267 | MORRISANIA AIR RIGHTS | 0 | 3 | 3 | Complex | 2023-08-29 | 2025-07-13 | Construction | 9738279.23 | 66235 | 9804514.23
6 | 11922 | 347 | HARRISON AVENUE REHAB (GROUP A) | 0 | 1 | 1 | Complex | 2023-07-30 | 2025-06-12 | Construction | 5108235 | 11983.76 | 5120218.76
6 | 10842 | 198 | BARUCH HOUSES ADDITION | 0 | 1 | 1 | Complex | 2023-12-13 | 2025-08-02 | Construction | 4634586 | 0 | 4634586
6 | 11924 | 287 | TWIN PARKS EAST (SITE 9) | 0 | 1 | 1 | Complex | 2023-10-27 | 2025-05-19 | Construction | 2928772 | 9115 | 2937887
6 | 12451 | 235 | MILL BROOK EXTENSION | 0 | 1 | 1 | Complex | 2023-10-02 | 2025-03-27 | Construction | 7998472 | 15270 | 8013742
6 | 12017 | 132 | WASHINGTON | 0 | 1 | 1 | Complex | 2023-09-10 | 2025-04-22 | Construction | 6185812.57 | 178391.4 | 6364203.97
TOTAL |  |  | TOTALS | 415 | 89 | 504 |  |  |  |  | 853880418.97 | 183665856.1 | 1069330916.89