## Summary
NYCHA Roof Repair Report - Reporting Period January 1, 2025 through December 31, 2025
The Roof Replacement Program entails 744 total roof replacements and repairs through CFY 2028, utilizing a total of $1.276 billion of City capital funds as well as other funding sources for a total budget of $1.672 billion. 597 roofs have been replaced as of December 31, 2025, including 122 completed in 2024. 147 roofs are still in progress as of December 31, 2025. Project information for these roofs in total is provided on the following sheet.

## Report
Tranche | Proj # | TDS | Development | Roofs Completed | Roofs Remaining | Total Roofs To Be Replaced | Complexity of Repair | Construction Start Date | Construction Completion Date (Actual or Forecast) | Current Phase | City Budget | Total Budget
2 | 7361 | 070 | CYPRESS HILLS | 15 | 0 | 15 | Complex | 2017-11-15 | 2019-12-11 | Completed | 15847397.27 | 19090242.21
2 | 7525 | 056 | BRUEKELEN | 32 | 0 | 32 | Complex | 2018-04-11 | 2024-10-24 | Completed | 51709277 | 74409451.64
2 | 8763 | 038 | SAINT NICHOLAS | 13 | 0 | 13 | Complex | 2018-02-01 | 2019-11-23 | Completed | 12723984 | 12740131.41
2 | 9052 | 045 | SEDGWICK | 7 | 0 | 7 | Complex | 2018-06-21 | 2019-10-26 | Completed | 9035127.2 | 9072298.44
2 | 9053 | 127 | WISE TOWERS | 2 | 0 | 2 | Complex | 2018-03-27 | 2019-02-20 | Completed | 7226030.81 | 7226030.81
2 | 9053 | 124 | WHITE** | 1 | 0 | 1 | Complex | 2018-03-27 | 2019-02-20 | Completed | 0 | 0
2 | 9055 | 096 | TILDEN | 8 | 0 | 8 | Complex | 2018-03-20 | 2020-01-10 | Completed | 9438883 | 10707757.86
3 | 9266 | 034 | EASTCHESTER GARDENS | 10 | 0 | 10 | Complex | 2019-01-03 | 2020-12-31 | Completed | 12259002 | 22230974.43
3 | 9267 | 141 | WEBSTER | 5 | 0 | 5 | Complex | 2019-02-18 | 2020-12-31 | Completed | 4769257.42 | 6992591.96
3 | 9272 | 032 | BRONX RIVER | 11 | 0 | 11 | Complex | 2018-07-13 | 2020-04-10 | Completed | 18519711.56 | 23165357.21
3 | 9279 | 028 | MELROSE | 8 | 0 | 8 | Complex | 2018-09-25 | 2020-12-31 | Completed | 11082441.07 | 22598158.21
5 | 10125 | 006 | VLADECK | 20 | 0 | 20 | Complex | 2022-06-30 | 2024-01-31 | Completed | 20151322.36 | 25167155.2
5 | 10126 | 007 | VLADECK II | 4 | 0 | 4 | Complex | 2022-07-01 | 2023-06-29 | Completed | 3324185.62 | 3664620.07
5 | 10127 | 120 | JACKSON | 7 | 0 | 7 | Complex | 2023-04-27 | 2025-01-21 | Completed | 15821715 | 15821715
5 | 10128 | 111 | DREW HAMILTON | 5 | 0 | 5 | Complex | 2023-05-16 | 2024-11-13 | Completed | 18660480 | 18660480
5 | 10129 | 043 | NOSTRAND | 17 | 0 | 17 | Complex | 2022-06-27 | 2024-09-23 | Completed | 39402979.81 | 39402979.81
5 | 10130 | 016 | BROWNSVILLE | 27 | 0 | 27 | Complex | 2022-06-16 | 2024-12-02 | Completed | 53413312 | 53413312
5 | 10133 | 033 | WOODSIDE | 9 | 0 | 9 | Complex | 2022-11-14 | 2024-11-12 | Completed | 28403738.31 | 28403738.31
3 | 9318 | 092 | BAY VIEW | 24 | 0 | 24 | Complex | 2018-01-31 | 2020-08-11 | Completed | 253846 | 20287925.95
3 | 9319 | 092 | BAY VIEW | 0 | 0 | 0 | Complex | 2018-01-31 | 2020-11-10 | Completed | 19374627 | 31125188.44
4 | 9934 | 131 | TOMPKINS | 8 | 0 | 8 | Complex | 2021-08-20 | 2024-04-28 | Completed | 19051174 | 24201367.76
4 | 9998 | 159 | HOLMES | 2 | 0 | 2 | Complex | 2021-08-26 | 2023-09-15 | Completed | 5779043 | 7150281.39
5 | 10131 | 020 | LINCOLN | 6 | 5 | 11 | Complex | 2024-05-06 | 2026-06-24 | Construction | 26115299 | 26115299
3 | 10113 | 157 | BRONX RIVER ADDITION*** | 0 | 0 | 0 | Complex | 2018-10-04 | 2020-09-15 | Completed | 0 | 77540
3 | 9861 | 502 | MORRIS II | 7 | 0 | 7 | Complex | 2019-05-11 | 2022-10-28 | Completed | 8264826.32 | 16025620.74
4 | 9927 | 088 | MONROE | 13 | 0 | 13 | Complex | 2021-03-29 | 2023-06-09 | Completed | 20166961.37 | 31051203.02
4 | 9930 | 021 | MARCY | 28 | 0 | 28 | Complex | 2021-04-19 | 2023-11-29 | Completed | 40046152 | 49155289.31
3 | 9378 | 271 | BORINQUEN PLAZA II | 7 | 0 | 7 | Complex | 2018-09-28 | 2019-11-24 | Completed | 7953742.96 | 8653159.81
4 | 9923 | 062 | WASHINGTON | 14 | 0 | 14 | Complex | 2021-05-27 | 2023-12-14 | Completed | 30495706 | 30647645.32
4 | 9924 | 008 | SOUTH JAMAICA I | 11 | 0 | 11 | Complex | 2021-04-19 | 2023-03-15 | Completed | 24002950.23 | 30142168.04
4 | 9925 | 066 | SOUTH JAMAICA II | 16 | 0 | 16 | Complex | 2021-05-05 | 2023-06-23 | Completed | 18898356.67 | 27701033.13
4 | 9926 | 100 | GOMPERS | 3 | 0 | 3 | Complex | 2021-05-03 | 2022-10-26 | Completed | 6491478 | 7175470.76
4 | 9928 | 029 | FARRAGUT | 10 | 0 | 10 | Complex | 2020-01-06 | 2022-10-03 | Completed | 23874954 | 28909603.11
4 | 9931 | 065 | BREVOORT | 13 | 0 | 13 | Complex | 2021-08-23 | 2023-10-31 | Completed | 22426885.53 | 24014193.51
4 | 9933 | 113 | BUTLER | 6 | 0 | 6 | Complex | 2021-03-29 | 2023-03-16 | Completed | 13656899 | 13932838.38
3 | 8838 | 087 | GRANT | 10 | 0 | 10 | Complex | 2018-10-03 | 2022-02-11 | Completed | 14272455.01 | 16889008.99
3 | 9377 | 243 | BORINQUEN PLAZA I | 10 | 0 | 10 | Complex | 2019-04-09 | 2021-03-12 | Completed | 6027809.01 | 20707042.22
4 | 9932 | 001 | FIRST HOUSES | 8 | 0 | 8 | Complex | 2023-05-08 | 2026-01-19 | Completed | 14890646 | 38302459.17
1 | 6724 | 036 | SHEEPSHEAD BAY | 16 | 0 | 16 | Complex | 2016-02-11 | 2018-08-10 | Completed | 14446414 | 16272758.96
6 | 10842 | 198 | BARUCH HOUSES ADDITION | 1 | 0 | 1 | Complex | 2023-12-13 | 8/2/2025 | Completed | 2317293 | 2317293
6 | 10841 | 169 | LOW HOUSES | 4 | 0 | 4 | Complex | 2022-12-27 | 2024-06-17 | Completed | 8310026.2 | 11144010
6 | 11899 | 582 | DOUGLASS II | 6 | 0 | 6 | Complex | 2024-03-14 | 2025-11-13 | Completed | 12864781 | 12864781
6 | 11900 | 148 | DOUGLASS ADDITION | 1 | 0 | 1 | Complex | 2023-12-18 | 2025-02-11 | Completed | 4154153 | 4154153
6 | 11902 | 315 | VANDALIA AVENUE | 3 | 0 | 3 | Complex | 2024-04-29 | 2025-08-07 | Completed | 10356155 | 10356155
6 | 11903 | 223 | TELLER AVENUE-EAST 166TH STREET2 | 1 | 0 | 1 | Complex | 2023-11-21 | 2025-03-26 | Completed | 4390287 | 4390287
6 | 11904 | 236 | COLLEGE AVE- EAST 165TH2 | 1 | 0 | 1 | Complex | 2023-11-01 | 2025-01-23 | Completed | 3247579 | 3525443.58
6 | 11897 | 061 | VAN DYKE I | 9 | 14 | 23 | Complex | 2024-03-11 | 2026-09-02 | Construction | 54597191.7 | 54597191.7
6 | 11898 | 082 | DOUGLASS I | 9 | 2 | 11 | Complex | 2024-03-18 | 2026-09-17 | Construction | 24468875 | 24468875
6 | 11905 | 515 | REHAB PROGRAM (DOUGLASS REHABS) | 3 | 0 | 3 | Complex | 2023-11-27 | 2025-03-10 | Completed | 6475028 | 6475028
6 | 11906 | 040 | GUN HILL | 6 | 0 | 6 | Complex | 2024-02-10 | 2025-09-10 | Completed | 19618199 | 19618199
6 | 11901 | 123 | CLINTON | 7 | 0 | 7 | Complex | 2023-07-22 | 2026-06-19 | Construction | 16108017 | 16108017
6 | 11907 | 326 | LOWER EAST SIDE I INFILL | 5 | 0 | 5 | Complex | 2024-09-19 | 2025-10-23 | Completed | 8167336 | 8167336
6 | 11908 | 547 | HARRISON AVENUE REHAB (GROUP B) | 4 | 0 | 4 | Complex | 2024-02-12 | 2025-07-29 | Completed | 7514515 | 7514515
6 | 11910 | 341 | UNIVERSITY AVENUE REHAB | 3 | 0 | 3 | Complex | 2023-08-21 | 2025-08-15 | Completed | 9164593 | 9722531.42
6 | 12295 | 367 | HUNTS POINT AVENUE REHAB | 8 | 0 | 8 | Complex | 2023-09-18 | 2025-08-03 | Completed | 18035280 | 18035280
6 | 11912 | 084 | MILL BROOK | 5 | 0 | 5 | Complex | 2024-05-24 | 2025-10-15 | Completed | 11780930 | 11780930
6 | 11913 | 192 | SEWARD PARK EXTENSION | 4 | 0 | 4 | Complex | 2024-03-07 | 2025-05-27 | Completed | 5961732 | 5961732
6 | 11914 | 174 | WSUR (SITE C) 589 AMSTERDAM AVE | 1 | 0 | 1 | Complex | 2023-10-25 | 2025-04-25 | Completed | 4580139 | 4580139
6 | 11909 | 178 | WSUR (BROWNSTONES) | 20 | 16 | 36 | Complex | 2024-03-14 | 2026-08-29 | Construction | 18196348 | 18196348
6 | 11916 | 168 | HUGHES APARTMENTS | 4 | 0 | 4 | Complex | 2023-12-27 | 2025-04-24 | Completed | 10463236 | 10463236
6 | 11917 | 102 | MORRIS I | 10 | 0 | 10 | Complex | 2024-04-26 | 2025-12-29 | Completed | 18124598 | 18124598
6 | 11919 | 093 | ST. MARY'S | 6 | 0 | 6 | Complex | 2023-12-26 | 2025-06-27 | Completed | 12812285 | 12812285
6 | 11920 | 267 | MORRISANIA AIR RIGHTS | 3 | 0 | 3 | Complex | 2023-08-29 | 2024-10-06 | Completed | 10456103 | 11045376.01
6 | 11921 | 362 | LONGFELLOW AVENUE REHAB | 2 | 0 | 2 | Complex | 2024-08-28 | 2025-11-05 | Completed | 9199849 | 9199849
6 | 11915 | 256 | ATLANTIC TERMINAL SITE 4B**** | 0 | 1 | 1 | Complex | TBD | TBD | Design | 36861.3 | 3862547.59
6 | 11923 | 129 | MOORE | 2 | 0 | 2 | Complex | 2024-02-15 | 2025-07-17 | Completed | 6622935 | 6622935
6 | 11924 | 287 | TWIN PARKS EAST (SITE 9) | 1 | 0 | 1 | Complex | 2023-10-27 | 2025-05-04 | Completed | 2455773 | 2937887
6 | 11918 | 182 | WOODSON | 0 | 2 | 2 | Complex | 2024-02-06 | 2026-03-01 | Construction | 5492713 | 5492713
6 | 12017 | 062 | WASHINGTON | 1 | 0 | 1 | Complex | 2023-09-10 | 2025-07-03 | Completed | 7782590 | 8740519.03
6 | 12451 | 132 | MILL BROOK EXTENSION | 1 | 0 | 1 | Complex | 2023-10-02 | 2025-01-23 | Completed | 3829473 | 3829473
7 | 13297 | 150 | 830 AMSTERDAM AVENUE | 1 | 0 | 1 | Complex | 2024-10-28 | 2025-09-08 | Completed | 3748091 | 3748091
6 | 11922 | 347 | HARRISON AVENUE REHAB (GROUP A) | 0 | 1 | 1 | Complex | 2023-12-01 | 2026-06-02 | Construction | 3454221 | 4946374.17
1 | 7366 | 505 | QUEENSBRIDGE NORTH | 13 | 0 | 13 | Complex | 2015-05-28 | 2016-06-16 | Completed | 28123611 | 44215418.07
1 | 7365 | 005 | QUEENSBRIDGE SOUTH | 13 | 0 | 13 | Complex | 2015-05-28 | 2016-09-08 | Completed | 27802029 | 48646182.14
6 | 11925 | 235 | BRYANT AVENUE-EAST 174TH STREET | 0 | 1 | 1 | Complex | 2024-06-12 | 2026-04-14 | Construction | 3067535 | 3067535
1 | 304 | 031 | ALBANY I | 6 | 0 | 6 | Complex | 2015-08-25 | 2017-04-21 | Completed | 9870447 | 49606505.52
1 | 304 | 085 | ALBANY II* | 3 | 0 | 3 | Complex | 2015-08-25 | 2017-04-21 | Completed | 0 | 0
7 | 13146 | 050 | LEXINGTON | 0 | 4 | 4 | Complex | 2025-08-10 | 2027-04-19 | Construction | 10170020 | 10170020
7 | 13144 | 039 | PELHAM PARKWAY | 0 | 23 | 23 | Complex | 2026-12-01 | 2028-08-05 | Design | 1523934 | 61523935
7 | 13145 | 193 | THROGGS NECK ADDITION | 0 | 4 | 4 | Complex | 2026-01-26 | 2027-10-01 | Procurement | 11793246 | 11947151.93
7 | 13142 | 103 | MCKINLEY | 0 | 5 | 5 | Complex | 2026-02-15 | 2027-09-20 | Procurement | 10309592 | 13668600
7 | 13140 | 245 | RANDALL AVENUE-BALCOM AVENUE | 0 | 3 | 3 | Complex | 2026-01-04 | 2027-08-25 | Procurement | 11913633 | 11913633
1 | 7363 | 047 | PARKSIDE | 14 | 0 | 14 | Complex | 2015-09-02 | 2017-06-30 | Completed | 14441872 | 34988920.97
7 | 13608 | 072 | HOWARD | 0 | 10 | 10 | Complex | 2026-04-03 | 2028-11-10 | Procurement | 15062206 | 28123250
7 | 13605 | 514 | WHITMAN | 3 | 12 | 15 | Complex | 2024-08-05 | 2027-10-05 | Construction | 28208838 | 44419901.6
7 | 14127 | 063 | THROGGS NECK | 0 | 29 | 29 | Complex | 2026-03-07 | 2029-08-29 | Procurement | 49105606 | 49105606
7 | 14386 | 024 | PATTERSON | 0 | 15 | 15 | Complex | 2026-04-07 | 2028-07-21 | Procurement | 41967028 | 43513454.73
TOTALS |  |  | 87 | 597 | 147 | 744 |  |  |  |  | 1276425852.73 | 1672018334.04
|  | * | Budget for Albany II captured under Albany I
|  | ** | Budget for White captured under Wise Towers
|  | *** | Roof Replacements for Bronx River Addition captured under Bronx River
|  | **** | Project on hold due to on-going facade work